## Tabelle1
Sprint Review Protocol
Sprint No: |  | 1
Date & Time |  | 2023-04-10
Group Number |  | 24
Participant 1 |  | Philipp Sawa
Participant 2 |  | Minu Kim
Participant 3 |  | Mateo Lufi
Participant 4 |  | Andrija Loisel
Participant 5
Mentor |  | Dinhof
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Create, Join, Permissions+Scope | 2 | 3 | 1 | 1 | 0 | Easy implementation - no problems
2 | Implement simple commands | 5 |  | -5
3 | Play Music from links | 7 |  | -7
4 | Implement more complex commands | 10 |  | -10
5 | Watch videos together API | 10 |  | -10
6 | create polls via bot | 5 |  | -5
7 |  |  |  | 0
7 |  |  |  | -36 | 1 | 1
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol