## Tabelle1
Sprint Review Protocol
Sprint No: |  | 1
Date & Time |  | 2023-04-10
Group Number |  | 24
Participant 1 |  | Philipp Sawa
Participant 2 |  | Minu Kim
Participant 3 |  | Mateo Lufi
Participant 4 |  | Andrija Loisel
Participant 5
Mentor |  | Dinhof
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Create, Join, Permissions+Scope | 2 | 3 | 1 | 1 | 1 | Easy implementation - no problems - CAUTION: Bot ended up being deleted. Project starting over from scratch - ran into issues.
2 | Technical Debt Sprint | 4 | 7 | 3 | 1 | 0 | New Bot creation - linking to VS File, implemented playing sound from Music file on Drive - goal: playing sound from music link, not file in next sprint
3 | Implement simple commands | 5 | 2 | -3 | 0 | 0 | Working on this part - can now read commands and reply, no action yet. Implementation within next few days. Very complex task.
4 | Play Music from links | 7 |  | -7
5 | Implement more complex commands | 10 |  | -10
6 | Watch videos together API | 10 |  | -10
7 | create polls via bot | 5 |  | -5
0
7 |  |  |  | -31 | 3 | 3
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol