## Tabelle1
Sprint Review Protocol
Sprint No: |  | 5
Date & Time |  | 2023-06-13
Group Number |  | 24
Participant 1 |  | Philipp Sawa
Participant 2 |  | Minu Kim
Participant 3 |  | Mateo Lufi
Participant 4 |  | Andrija Loisel
Participant 5
Mentor |  | Dinhof
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Create, Join, Permissions+Scope | 2 | 3 | 1 | 1 | 1 | Easy implementation - no problems - CAUTION: Bot ended up being deleted. Project starting over from scratch - ran into issues.
2 | Technical Debt Sprint | 4 | 7 | 3 | 1 | 0 | New Bot creation - linking to VS File, implemented playing sound from Music file on Drive - goal: playing sound from music link, not file in next sprint
3 | Implement simple commands | 5 | 2 | -3 | 1 | 1 | Can now read commands and reply
4 | Play Music from links | 7 | 16 | 9 | 1 | 2 | Still not done - issue with RegEx, implementing an audio player biggest hurdle. Sometimes works, sometimes doesn't, even with the same link. Troubleshooting + technical debt sprint soon
5 | Implement more complex commands | 10 | 12.5 | 2.5 | 1 | 0 | Implemented weather & currency conversion via API, reading user info from the server, showing links / responding to messages with information
6 | Watch videos together API | 10 | 18.5 | 8.5 | 2 | 3 | API Problems - Video doesn't load, Video doesn't skip, Room doesn't exist, etc. - A lot of troubleshooting & Fixing.
7 | create polls via bot | 5 | 3 | -2 | 1 | 0 | No further issues with implementation
8 | Final Technical Fixes | 9 | 6.5 | -2.5 | 1 | 0 | Bugfixes - Audioplayer, Expired API issues, added commands, fixed layout problems within code
8 |  |  |  | 16.5 | 8 | 8
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol